## Dev
PPC CBE – Development Tracker
S.no | Module | Task | Owner | Status | Dependencies | Priority | Blocker/Notes | Start Date | End Date | Progress (%)
|  |  |  | Not Started |  | High
|  |  |  | In Progress |  | Low
|  |  |  | Completed |  | Medium
Blocked
On Hold

## Requirement Sheet
PPC CBE ¦ Requirement Sheet
S.no | Module / Feature | Requirement ID | Requirement Description | Business Requirement | Functional Requirements | User Flow / Process Flow | UI / Frontend Requirements | Backend Requirements | Database Requirements | API Requirements | Integration Requirements | Technology / Architecture | Non-Functional Requirements | Dependencies | Assumptions | Constraints | Validation / Business Rules | Error / Exception Handling | Security Requirements | Performance Requirements | Open Questions / Clarifications | Acceptance Criteria | Priority | Status | Open Questions / Clarifications | Owner
[23 empty] | High | Draft
[23 empty] | Medium | Approved
[23 empty] | Low | Reviewed
In Development
Completed

## Module-Wireframe-Draft
# | Modules | Current Workflow / Discussed Points | Action | Explained By
1 | SAP Data Integration (Material Outward) | The application first pulls all dispatched material data from SAP. Only the materials that were dispatched from Titan to Vendors will be available in the application. | Yet to Confirm with SAP team | Vengatesh
2 | Material Outward Process | Titan dispatches the material to the Vendor for processing. | Confirmed | Vengatesh
3 | Vendor Process | Vendor performs the required polishing process on the received materials. | Confirmed | Vengatesh
4 | Titan QC Visit | Titan QC team visits the Vendor location and performs the quality checking of the processed materials. | Confirmed | Vengatesh
5 | QC Completed & Vendor Packing | After QC completion, the Vendor packs the approved materials by placing the Front and Back materials from the Blue Tray into the White Box. | Confirmed | Vengatesh
6 | Audit Sheet Preparation | The Vendor fills and completes the Audit Sheet for the packed materials. | Confirmed | Vengatesh
7 | Core Inward Process Begins | The actual inward process starts after the material reaches Titan. | Confirmed | Vengatesh
8 | Material Dispatch to Titan | After packing, the Vendor dispatches the White Box, Audit Sheet and Delivery Challan (DC) to Titan through Transport. | Confirmed | Vengatesh
9 | Transportation | The transport vehicle carries the material from the Vendor location to the Titan factory. | Confirmed | Vengatesh
10 | Gate Security Entry | The transport vehicle reaches the Titan Gate Security for Seal Verification and to confirm the receipt of the material before allowing entry into the sub-con. | Confirmed | Vengatesh
11 | Gate Verification | Gate Security verifies the Delivery Challan (DC), Security Rope (Store-In Rope), and Security Seal before allowing the material into the factory. | Confirmed | Vengatesh
12 | Gate Security Approval | After successful verification of the DC, Rope, and Seal, Gate Security approves the entry into the factory premises. | Confirmed | Vengatesh
13 | Gate Entry System | Gate Security records the inward entry in the online Gate Entry system. This online system is available only at the Gate Security. | Confirmed | Vengatesh
14 | DC Handover to Sub-con | After Gate approval, the Delivery Challan (DC) and material are handed over to the Sub-con team. | Confirmed | Vengatesh
15 | Register Entry | The material details are manually entered into the Sub-con register after receiving the material from Gate Security. | Confirmed | Vengatesh
16 | Sub-con Receiving (Material Inward) | The material reaches the Sub-con area, which is the destination for the inward process. | Confirmed | Vengatesh
17 | Receiving Category | The received material is categorized as Regular or Rework before starting the verification process. | Confirmed | Vengatesh
18 | QC Acknowledgement | After the material is received at the Sub-con, the QC team marks the acknowledgement status as "Done" | Confirmed | Vengatesh
19 | DC Restriction | A single DC is allowed to contain a maximum of 13 line items. | Confirmed | Vengatesh
20 | Multiple DC | If the quantity contains more than 13 line items, it has to be split into two or more DCs. | Confirmed | Vengatesh
21 | Excess & Less | During verification, the material quantity is identified as Excess or Less. | Confirmed | Vengatesh
22 | Excess Case | If the received quantity is Excess, there are no issues and the process continues. | Confirmed | Vengatesh
23 | Less Case | If the received quantity is Less, the received DC is reverted back to the Vendor. | Confirmed | Vengatesh
24 | Vendor Confirmation | The Vendor is informed through email that the DC has been reverted. | Confirmed | Vengatesh
25 | Vendor Modification | The Vendor accepts the reverted DC, modifies it, and sends the corrected DC back to Titan through email. | Confirmed | Vengatesh
26 | SAP Format Change | After receiving the corrected DC, the document format is manually changed to match the SAP upload format. This activity approximately consumes 2 to 3 minutes. | Confirmed | Vengatesh
27 | Physical Counting | Excess Case: Physical counting of the material is performed. This process approximately consumes 35 minutes. | Confirmed | Vengatesh
28 | Level Movement | Once the acknowledgement is marked as Done, the received stock is moved from Level 2 to Level 1. | Confirmed | Vengatesh
29 | Sub-con Process | After the material reaches Level 1, the Sub-con team takes the Level 1 material and performs UD Post in SAP. | Confirmed | Vengatesh
30 | UD Post | UD Post will be update by the Sub-con team in SAP. | Confirmed | Vengatesh
31 | SAP 313 Waiting | After the UD Post is completed, the material remains in SAP 313 under the status Finished Goods, waiting for the next process. | Confirmed | Vengatesh
32 | Manual Data Preparation | The UD Posted material details are copied from the manual document into Excel. | Confirmed | Vengatesh
33 | SAP 313 Format Conversion | The copied Excel data is manually reformatted to match the SAP 313 upload format. | Confirmed | Vengatesh
34 | SAP 313 Document Preparation | The updated Excel file is prepared based on the SAP 313 required format. | Confirmed | Vengatesh
35 | Print Document | The updated SAP 313 document is printed. | Confirmed | Vengatesh
36 | Signature Approval | The required signatures are obtained on the printed SAP 313 document. | Confirmed | Vengatesh
37 | Physical Material Verification | Using the signed SAP 313 document, the PPC team member physically verifies the material before collecting it from the Sub-con Tray | Confirmed | Vengatesh
38 |  | Print → Signature → Material Check → Kept in Sub-con Tray → PPC Team Member takes it → Verifies again before storing into PPC | Confirmed | Vengatesh
39 | PPC Verification | Before storing the material into PPC, the PPC team member verifies and validates the material once again. | Confirmed | Vengatesh
40 | Sub-con Tray | After successful physical verification, the Sub-con team keeps the material in the Sub-con Tray for collection by the PPC team member. | Confirmed | Vengatesh
41 | PPC Collection | The PPC team member collects the material from the Sub-con Tray. The material is not directly moved into PPC Storage. | Confirmed | Vengatesh
42 | Sub-con Completion | Once the PPC team member collects the material from the Sub-con Tray, the Sub-con process ends. | Confirmed | Vengatesh
43 | QA Inspection | QA checks the material under the process called Inspection Cost with Outstanding. | Confirmed | Vengatesh
44 | Inspection Status | The material status is marked as Waiting for Inspection. | Confirmed | Vengatesh
45 | Quality Team | At this stage, the material is pending with the Quality Team. | Confirmed | Vengatesh
46 | QC Completion | After the Quality Team completes QC, the material is moved to Level 1 (ZQMTL1). | Confirmed | Vengatesh
47 | ZQMTL1 Material Checking | Material checking is performed at ZQMTL1. | Confirmed | Vengatesh
48 | Excel Preparation | Material data is copied into Excel and the format is manually changed to match the SAP upload format. | Confirmed | Vengatesh
49 | UD Post by Sub-con | The updated Excel data is uploaded into SAP, and UD Post is completed by the Sub-con Team. | Confirmed | Vengatesh
50 | Post UD Movement | After UD Post, the material in ZQMTL1 is moved to SAP 313. | Confirmed | Vengatesh
51 | 313 Process & Storage | A printout is taken, signatures are obtained, and the material is moved to Storage after completion of the SAP 313 process. | Confirmed | Vengatesh
52 | Plating | Process yet to be confirmed by the Titan team | Yet to Confirm by Titan Team | Vengatesh
53 | Return | Process yet to be confirmed by the Titan team | Yet to Confirm by Titan Team | Vengatesh

## Scanner Info
Scanner / Device | Purpose
Zebra LI4278 1D Wireless Scanner | Quick barcode scanning at inward, transfer, and material issue points.
Zebra MC2700 Scanner with Display | Scan, view, verify, and update application data directly on the device.
Zebra ZD230T Barcode Printer | Print Box UID and material identification barcode labels.
Argox Barcode Scanner | General barcode/QR scanning for material identification and traceability.

## Doc & Email Generation Point
# | Module | Action / Functional |  |  |  |  | Doc Generation |  |  |  | Mail
|  | Fields |  | Inputs | Landing To | How it Works | DC | PO | Audit | Upon Verification | From | To | CC | Mail Template
M1 | Login | Username |  | User Input
|  | Password |  | User Input
|  | Login Button |  | Button / Action | Dashbaord
M2 | Dashboard | Analytics |  | Dynamic | Menu Panel
M3 | SAP Data [P1: Data Table] | DC | Yet to Confirm | API Integration
|  | PO | Yet to Confirm | API Integration
|  | Material Info: Model | Yet to Confirm | API Integration
|  | Material Info: Version | Yet to Confirm | API Integration
|  | Total Batch Qty (Front + Back) | Yet to Confirm | API Integration
|  | Total Frontcase Qty | Yet to Confirm | API Integration
|  | Total Backcase Qty | Yet to Confirm | API Integration
|  | Vendor Name | Yet to Confirm | API Integration
|  | Timestamp: Material Sent | Yet to Confirm | API Integration
M4 | Material Outward [P2: Data Table] | Dispatched Vendor Batches (Status: Dispatched)
| - Titan QC (in Vendor Place) | QC Info | Yet to Confirm
| - Vendor Audit Sheet | Box UID WBX0000 (Additional Column in Vendor Audit Sheet)
| - Vendor Packing | Activity
| - Barcode Label | Sending with barcode label
M5 | Sub - Con (Material Inward) - [P3: Data Table] | Data/Doc Import to Application
- Vendor Confirmation (No Deviation/ Exists)
| - Accepted Components - Ahead Invoice via mail | Status: Moved to Next Module Rejected - Stay in the same M5
Sub Module: Reject
- Sub-con ack in SAP
| 313 - Printout | Material check physically
Sub-con tray (PPC)
| PPC Member Check | Check and store
Document Points
| SAP Data conver - from excel | Delaying (Current Process)
| Physical Qty count | Delaying (Current Process)

## D1
# | Module | Module Name | Functions | Main Fields
1 | M1 | Login | Login, Forgot Password, Logout, Role-based Access | Username, Password
2 | M2 | Dashboard | Dashboard Summary, Pending Tasks, Search, Quick Navigation, KPI Cards | Inward Count, Pending QC, Pending SAP, Pending Vendor, Waiting Inspection, Material Availability
3 | M3 | SAP Material Outward | SAP Sync, View Dispatched Materials, Search, Filter, View Details | SAP Document No, DC No, Vendor, Material Code, Model, Description, Quantity, Dispatch Date, Status
4 | M4 | Material Receiving (Sub-con Inward) | Receive Material, Select Category, Scan White Box, Scan DC, Scan Audit Sheet, View SAP Data | Receiving Category, White Box UID, DC No, Vendor, Audit Sheet No, Material, Model, Quantity, Received Date
5 | M5 | DC Verification | Verify DC, Compare with SAP, Validate Line Items, Approve DC | DC No, SAP Document No, Vendor, Total Line Items, Verification Status
6 | M6 | Physical Verification | Scan White Box, Verify Material, Verify Quantity, Verify Model, Confirm Verification | White Box UID, Material, Model, Expected Qty, Actual Qty, Verification Result, Verified By, Verified Date
7 | M7 | Deviation Management | Raise Deviation, Excess Handling, Less Handling, Revert DC, Send Vendor Mail, Vendor Confirmation | Deviation No, DC No, Vendor, Deviation Type, Expected Qty, Actual Qty, Difference Qty, Reason, Mail Status, Vendor Status
8 | M8 | QC Acknowledgement | QC Acknowledge, Mark Done, Trigger Level Movement | DC No, QC Status, Acknowledged By, Acknowledged Date
9 | M9 | SAP Processing | UD Post Status, SAP 313 Status, Upload Status, Posting History | SAP Document No, UD Post Status, SAP 313 Status, Posted By, Posted Date, Remarks
10 | M10 | PPC Collection & Verification | Collect Material, Verify Material, Confirm Collection, Complete Sub-con Process | Tray No, Material, Model, Quantity, Collected By, Collection Date, Verification Status
11 | M11 | QA Inspection | Inspection Queue, Start Inspection, Complete Inspection, Update Status | Material, Model, Inspection Status, QA User, Inspection Date
12 | M12 | ZQMTL1 Processing | Material Check, UD Post, Move to SAP 313 | Material, Model, Quantity, ZQMTL1 Status, SAP Status
13 | M13 | Storage Management | Assign Rack, Assign Bin, QR Scan, Location Search, Store Material | White Box UID, Rack, Row, Bin, Storage Location, Stored By, Stored Date
14 | M14 | Reports | Inward Report, Vendor Report, QC Report, SAP Report, Deviation Report, Storage Report | Date, Vendor, DC No, Material, Model, Status
15 | M15 | Masters | Vendor Master, Material Master, Model Master, Rack Master, Bin Master, User Master, Role Master | Master-specific fields
16 | M16 | Settings | User Management, Role Management, SAP Configuration, Mail Configuration, QR Configuration, Audit Logs | User, Role, SAP Settings, Mail Settings, QR Settings

## Current workflow
Current Workflow (General)
# | Process Stage | Activity | Output
1 | Raw Material Receipt | Raw materials received from supplier | Material available for verification
2 | DC & Invoice Verification | DC matched against invoice and paid invoice details | Verified material
3 | Dimension Verification | Physical dimensions checked as per specifications | Accept / Reject
4 | Rejection Handling | Rejected components recorded with remarks in email (damage, dirt, defect, etc.) and dropped from process | Rejected material
5 | Inward Processing | Accepted components moved to internal production flow | Components available for manufacturing
6 | Press shop Department | Internal operations performed (Stages 1–10) | Semi-processed components
7 | Machine Shop | Machining operations performed (Stages 11–20) | Machined components
8 | Vendor Decision Point | Based on process requirement, quantity and quality requirements, components may be sent to vendors | Vendor/Internal processing
9 | Vendor Verification | Quantity and component type verification before dispatch to vendor | Approved vendor lot
10 | Vendor Processing | External processing performed by vendor if required | Processed components
11 | Direct Closure Scenario | Some components may complete processing before Stage 20 (e.g., Stage 13) and directly move to final closure at Stage 20 | Closed manufacturing cycle
12 | Final Internal Completion | Components completing all machine shop stages proceed to next manufacturing phase | Ready for finishing process

## Phase-1 Req Disc - June 10th
Phase 1 - Requirement Discussion
# | Process Stage | Activity Description | Accept Flow | Reject Flow
1 | Polishing Outward Creation | Cases received from Machine Shop are grouped and prepared for vendor dispatch. Components are segregated based on model and process requirements. | Move to tray preparation | N/A
2 | Tray Preparation & Segregation | Front Cases and Back Cases are packed separately. Small and large cases will be maintained in different trays for tracking. | Sent to vendor | N/A
3 | Vendor Dispatch | Outward challan generated and trays dispatched to polishing vendor. Quantity verification performed before dispatch. | Vendor receives material | Dispatch discrepancy investigation
4 | Vendor Polishing Process | Vendor performs polishing operations to achieve required surface finish and appearance. | Move to vendor QC | Rework at vendor
5 | Vendor QC Inspection (Titan QC Team) | After polishing is completed, Titan QC personnel visit or inspect at the vendor location. They verify surface finish, scratches, dents, polishing marks and overall appearance before accepting the lot. QC tags will be attached for traceability. | Approved trays are released for inward movement back to Titan | Rejected components are sent back to the vendor for rework/polishing correction
6 | Polishing Inward Receipt | Polished trays received back from vendor. Quantity and tray verification performed against outward records. | Move to Titan QC | Quantity mismatch investigation
7 | Titan QC Inspection | Titan QC team performs detailed inspection on polishing quality and workmanship. Attached QC tags will be reviewed internally | Move to next process | Rejection recorded
8 | Rework Management | Rejected components are classified with rejection reasons such as scratches, dents, poor finish, damage, etc. | After rework return to QC | Scrap or hold decision
9 | Case Matching & Assembly Preparation | Front Case and Back Case are brought together for further processing. Proper model/version matching is verified. | Move to verification QC | Mismatch correction
10 | Version Mix-Up Check | Random and sample-based inspections are performed to ensure incorrect variants or models are not mixed together. | Approved for plating | Segregation and correction
11 | Plating Color Outward | Approved cases are sent for plating process based on required color specifications. | Move to plating vendor/process | N/A
12 | Plating Process | Surface color plating is performed according to model requirements. | Move to plating QC | Rework at plating stage
13 | Plating QC Inspection | Quality checks performed for color consistency, coating quality, finish, and visual appearance. | Move to assembly | Rejected for replating
14 | Re-Plating/Rework | Failed components are sent back for plating correction and re-inspection. | Return to QC | Scrap/Hold if repeatedly failing
15 | Final Assembly Release | Accepted plated cases are released to assembly where watch components will be assembled. | Assembly completed | N/A

## Titan Data
As of 16-06-2026, we have dispatched the following models and their respective quantities. Kindly acknowledge receipt upon arrival and confirm whether the quantities are correct or if there is any shortage or excess. Please do the needful.

|  |  |  | TOTAL QTY | 552
DC Date | DC No. | OUTPUT STOCK No. | Challan No | Challan Input Date | Delivery Qty | Input Stock No. | PO No. | Remarks
16-06-2026 | KRCC-152 | 10017SCB02 | 3003063702 | 13-05-2026 | 9 | 10017XXB02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-153 | 1829SDE02 | 3003065223 | 22-05-2026 | 2 | 1829XXE02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-153 | 10090SDA02 | 3003065885 | 26-05-2026 | 2 | 10090XXA02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1043SBD02 | 3003068629 | 2026-12-06 | 8 | 1043XXD02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 10065SDD02 | 3003065400 | 23-05-2026 | 1 | 10065XXD02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1829SDE02 | 3003065223 | 22-05-2026 | 1 | 1829XXE02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 90140SDB02 | 3003064799 | 20-05-2026 | 2 | 90140XXB02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1829SDM02 | 3003065677 | 25-05-2026 | 1 | 1829XXM02/35 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 90106SDC02 | 3003065677 | 25-05-2026 | 3 | 90106XXC02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 90174SCB02 | 3003067715 | 2026-08-06 | 5 | 90174XXB02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1805SAG02 | 3003067454 | 2026-05-06 | 4 | 1805XXG02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 2777SAA02 | 3003064602 | 19-05-2026 | 1 | 2777XXA02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 10077SCA02 | 3003061734 | 30-04-2026 | 1 | 10077XXA02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1878SAB02 | 3003067060 | 2026-03-06 | 1 | 1878XXB02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 1828SDE02 | 3003066753 | 2026-01-06 | 3 | 1828XXE02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-154 | 10077SCB02 | 3003064602 | 19-05-2026 | 2 | 10077XXB02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-156 | 1595SAG02 | 3003056794 | 2026-02-04 | 129 | 1595XXG02/20 | 801005439 | POLISHING COMPLETED
16-06-2026 | KRCC-156 | 1595SAG02 | 3003067715 | 2026-08-06 | 377 | 1595XXG02/20 | 801005439 | POLISHING COMPLETED

|  |  |  | TOTAL QTY | 1072
DC Date | DC No. | OUTPUT STOCK No. | Challan No | Challan Input Date | Delivery Qty | Input Stock No. | PO No. | Remarks
16-06-2026 | KRCC-155 | 2819XXA02/20 | 3003056794 | 2026-02-04 | 46 | 2819XXA02/20 | 801005439 | WITHOUT PROCESS
16-06-2026 | KRCC-155 | 2819XXA02/20 | 3003067968 | 2026-09-06 | 25 | 2819XXA02/20 | 801005439 | WITHOUT PROCESS
16-06-2026 | KRCC-155 | 2819XXA02/20 | 3003069064 | 15-06-2026 | 1001 | 2819XXA02/20 | 801005439 | WITHOUT PROCESS

|  |  |  | TOTAL QTY | 2
DC Date | DC No. | OUTPUT STOCK No. | Challan No | Challan Input Date | Delivery Qty | Input Stock No. | PO No. | Remarks
16-06-2026 | KPL-0047 | 10011SCD02/R | 3003061021 | 27-04-2026 | 2 | 10011SCD02/R | 801005522 | PLATING REWORK COMPLETED

## MOM
Project Title | PPC CBE - Inventory Tracking & Process Digitization
Date | 2026-07-03 | Titan | Pinesphere
Start Time | 11:30 | Vengatesh | Kauverysree
End Time | 12:09 |  | Dencil Jaushmy
Duration | 40 min | Santhosh | Shalini Preetha
Location | Microsoft Teams

## Scanning Points
Stage | Activity | QR Scan
1 | Vendor Inward (Dispatch Creation) | No scan
2 | Vendor Processing & White Box Packing | QR/White Box ID generated and attached to box
3 | Gate Entry | Scan White Box QR
4 | Document Verification | Uses data from White Box QR scanned at Gate Entry
5 | Physical Verification | Scan White Box QR
6 | SAP GRN (101) | No scan
7 | Quality Inspection (321) | Scan White Box QR
8 | Bin Transfer (313) | Scan White Box QR + Source Bin QR + Destination Bin QR
9 | Location Mapping & Storage | Scan White Box QR + Rack QR + Bin QR
10 | Dashboard | No scan (display only)
11 | Material Issue to Production | Scan White Box QR + Rack QR
12 | Deviation Management | Triggered from verification stages

## Meeting Draft
DB
|  |  |  | Batch ID |  | Scenario 1 |  |  |  | Scenario 2
Stage 1 | PO | API | SAP | DC | Sucess | Stage 3: Inward - White box scanning (Each Box Scanning) |  |  |  | Stage 3: Inward - White box scanning (Each Box Scanning)
|  |  |  | Audit |  | Bar Code Data |  |  |  | Bar Code Data
Stage 2 | DC Import |  |  |  |  | Bar Code | UID | Application Layer |  | Bar Code | UID | Application Layer
| Audit Sheet Import |  |  |  |  | Batch ID |  | Check with PO -> API -> SAP |  | Batch ID |  | Check with PO -> API -> SAP
[6 empty] | Model Num |  | Check with PO -> API -> SAP |  | Model Num |  | Check with PO -> API -> SAP
[6 empty] | Vendor Name |  | Check with PO -> API -> SAP |  | Vendor Name |  | Check with PO -> API -> SAP
[6 empty] | Received Date |  | From Vendor (Titan QC Team) |  | Received Date |  | From Vendor (Titan QC Team)
[6 empty] | Front Case |  | Check with PO -> API -> SAP |  | Front Case |  | Check with PO -> API -> SAP
[6 empty] | Back Case |  | Check with PO -> API -> SAP |  | Back Case |  | Check with PO -> API -> SAP
[6 empty] | Accept Qty |  | Check with PO -> API -> SAP -- [500-250] |  | Accept Qty |  | Check with PO -> API -> SAP -- [500-250]
[6 empty] | Reject Qty |  | Check with PO -> API -> SAP -- [500-40] |  | Reject Qty |  | Check with PO -> API -> SAP -- [0]
[6 empty] | Total Received |  | Check with PO -> API -> SAP -- [460] | In DB - Shortage = 0 | Total Received |  | Check with PO -> API -> SAP -- [460] | In DB - Shortage = 40
[6 empty] | Action |  | Store in DB Temporarily & Permanent on "Submit" |  | Action |  | Store in DB Temporarily & Permanent on "Submit"
Application Level Data
On Submit
Mail
Reports

## Post WHM Shift
# | Dept | Process | Current / Shift | Post WHM / Shift | Remarks | Application Level
1 | Sub-con | Material Inward | 200 min | 30 min | Barcode scan and digital inward eliminate manual entry and duplicate recording. | 1. Operator scans the Box UID. 2. The application fetches the linked inward details such as Vendor, Date, Model and Quantity and creates/updates the inward transaction instead of entering the same material details manually.
2 | Sub-con | Manual Verification (Titan DC & Vendor DC) | 400 min | 20 min | Automatic DC matching with Vendor DC and SAP; only exception cases need manual verification. | 1. On /UID scan, the application retrieves the linked transaction and document details. 2. The user verifies DC, PO, Audit Sheet and mail reference in the application and the system validates the material details against the available transaction data.
3 | Sub-con | Accepted Qty & Rejected Qty (Quality Audit Sheet) | 100 min | 30 min | Audit data captured digitally through scanning instead of manual recording. | 1. QC result is recorded in the application against the inward/material transaction. 2. The application maintains the approved/rejected status and quantity against the scanned material record. 3. Rejected material is prevented from proceeding to storage.
4 | Sub-con | GRN Posting Inward (SAP 101) | 40 min | 5 min | SAP posting details are pulled into the application, reducing manual verification and tracking effort | 1. After SAP 101 posting, the application pulls the relevant SAP inward/GRN record. 2. The application displays and links the SAP posting details and material document number against the inward transaction
5 | Sub-con | Communication to QC Team (Mail Alert & Verbal) | 100 min | 10 min | System sends automatic mail notifications; only follow-up communication if required. | 1. The inward transaction/status is available in the application workflow for the next QC stage. 2. QC can identify material pending for quality verification from the application status instead of depending only on verbal communication.
6 | Sub-con | QD Post (SAP 321) | 100 min | 20 min | Integrated SAP transaction with reduced manual intervention. | 1. SAP 321 posting is completed in SAP after quality clearance. 2. Application pulls the SAP 321 posted record/status and updates the corresponding material transaction
7 | Sub-con | Attach Document Along with Box | 600 min | 20 min | Physical document attachment eliminated; documents linked digitally using . | 1. Documents are digitally linked to the inward transaction and Box UID. 2. Scanning the Box UID retrieves the linked transaction and document details for verification.
8 | Sub-con | Bin Transfer (SAP 313) | 200 min | 45 min | scan-based transfer with automatic validation. | 1. The application tracks the CBSC to CBFC transfer through scanning. 2. Application pulls the SAP 313 posted record/status and updates the corresponding material transaction
9 | Sub-con | Printout from SAP after SAP 313 | 40 min | 5 min | Printing required only for exceptional or audit cases. | 1. The application stores the SAP material document/posting confirmation against the transaction. 2. The transfer status and SAP reference can be checked from the digital transaction record.
10 | Sub-con | Attach Document Along with Box | 60 min | 5 min | Digital document linkage removes physical attachment. | same as No.7
11 | Sub-con | Bin Transfer (313) | 100 min | 25 min | Faster scanning and confirmation through WHM workflow. | 1. User scans the Box UID to identify the material transfer transaction. 2. Application validates the transaction and records the transfer status linked to the SAP 313 posted record.
12 | Sub-con | Communicate to CBFC Team | 40 min | 5 min | Automatic status notification through the application. | 1. Once the transfer is completed, the status is updated in WHM. 2. CBFC can view the material ready for storage based on the transaction status.
13 | CBFC | CBFC Manual Count | 45 min | 20 min | Quantity verified through traceability; only validation count required. | 1. Scan the Box UID to view the recorded model and quantity. 2. User verifies and confirms the physical quantity; mismatches are recorded in application
14 | CBFC | Location Identification Input | 80 min | 10 min | Rack/Bin location available instantly through the system. | 1. Application displays available Rack/Bin space during storage. 2. User scans the Rack/Bin and confirms the material storage location
15 | CBFC | Picking (In-house) | 180 min | 20 min | System guides operator to exact Rack–Row–Bin location, reducing search time. | 1. WHM displays the stored Rack–Row–Bin location for the required material. 2. Operator locates and scans the material for validation and pick confirmation
16 | CBFC | Deliver (In-house & Bought Out) | 180 min | 30 min | Digital confirmation and traceability reduce manual documentation. | 1. Operator scans and verifies the material details. 2. Issue/delivery is confirmed, and the movement status is recorded in WHM
17 | CBFC | Spare & Replacement | 120 min | 20 min | Material traceability and location visibility reduce retrieval time. | 1. User searches the required material and application displays its stored Rack/Bin location. 2. Operator scans the material and confirms the issue/movement in WHM

## Draft Module List
# | Module | Flow
1 | Vendor Outward | Vendor completes polishing, packs materials in a white box with Audit Sheet/DC, and dispatches to Titan.
2 | Vendor Notification | Vendor sends packing confirmation and shipment details to Titan through email.
3 | Material Inward | Scan Box UID/DC, validate against SAP PO, and verify vendor documents before inward processing.
4 | Physical Verification | Verify model, quantity, and audit sheet against the received material and identify deviations.
5 | Deviation Management | Log deviations, notify the vendor, and receive vendor acceptance or correction before proceeding.
6 | Vendor Acceptance | Vendor confirms "No Abnormal / Accepted" through email, allowing invoice processing and material acceptance.
7 | SAP GRN (101) | Generate Goods Receipt in SAP after successful verification and vendor confirmation.
8 | Quality Inspection (321) | Perform QC inspection and update the material quality status in SAP.
9 | Bin Transfer (313) | Transfer approved material from CBSC to CBFC through barcode scanning and SAP posting.
10 | Material Storage & Rack Space Suggestion | Place the material in the suggested rack/bin location and update the exact storage location. Scan the rack to display available occupancy and recommend the best storage location automatically.
11 | Material Search | Scan any ID (Vendor ID, Vendor Name, Model No, DC No, or Box UID) to locate the material instantly.
12 | Material Issue | Scan, locate, pick, and issue materials based on production requirements with location validation.
13 | Finished Goods Confirmation | Finished Goods team confirms case assembly completion and posts the confirmation in SAP.
14 | Dashboard & Reports | Display stock availability, rack occupancy, pending verification, deviations, vendor responses, and movement history in real time.
15 | User Management
16 | Reports

## Req SAP DAta
# | SAP Data | Why Needed
1 | Delivery Challan (DC) | Verify the vendor delivery. | Kauvery
2 | Purchase Order (PO) | Validate the inward material. | Kauvery
3 | Vendor Master | Validate the supplier. | Kauvery
4 | Movement Types - 101 | Goods Receipt | Kauvery
5 | Movement Types - 313 | Stock Transfer | Kauvery
6 | Movement Types - 321 | Quality to Unrestricted Stock | Kauvery
7 | Material Document Number | Store the SAP reference after posting. | Kauvery
8 | Inventory/Stock Movements | Material movement history | Kauvery
9 | Open PO / Pending Quantity | Pending receipt information | Kauvery
Application Data
| Box ID (Batch ID) | Application | New Solution | Label (Vendor Place - Marked in QED Sheet)